## Plan
[6 empty] | 2018-07-30 | v4.7
St1 Deep Heat Oy
Stimulation Plan
Day | Stim Stage | Pumping stage | Hours | Well Head Pressure bar(g) | Flow l/min | Planned Volume m3 | Actual Volume m3 | Note
1 | 1 | 1 | 2 | 750 | 400 | 48 | 65.2 | Between every pumping stage keep 2 hour shut-in pause.
1 | 1 | 2 | 5 | 750 | 400 | 120 | 120
1 | 1 | 3 | 5 | 750 | 400 | 120 | 120 | Record open and shut-in pressures all the time.
2 | 1 | 4 | 12 | 750 | 400 | 288 | 288
2 | 1 | 5 | 10 | 750 | 400 | 240 | 240 | Depressurize well during 0 pumping days.
3 | 1 |  | 24 | 0 | 0 | 0 | -42.2
4 | 1 | 6 | 24 | 820 | 400 | 576 | 576 | Record flow out all the time when bleeding off.
5 | 1 | 7 | 12 | 820 | 400 | 288 | 288.6
6 | 1 | 8 | 36 | 820 | 400 | 864 | 870 | In the beginning and at the end of each stimulation stage
8 | 1 | 9 | 18 | 820 | 400 | 432 | 432 | perform a leak off test to see rock transmissibility.
9 | 1 |  | 24 | 0 | 0 | 0 | -112.7
10 | 1 | 10 | 32 | 900 | 600 | 1152 | 1158.2 | Formation leaking pressure around 400 bars when stage
11 | 1 | 11 | 24 | 0 | 0 | 0 | -206.5 | is changed.
12 | 2 | 1 | 12 | 750 | 800 | 576 | 576 | Stages 2-5 shall be determined according to the results
12 | 2 | 2 | 12 | 750 | 800 | 576 | 576 | on stage 1.
13 | 2 | 3 | 24 | 750 | 1000 | 1440 | 1440
14 | 2 | 4 | 24 | 750 | 1000 | 1440 | 1440 | Formation leaking pressure around 400 bars when stage
15 | 2 |  | 24 | 0 | 0 | 0 | -100 | is changed.
16 | 3 | 1 | 12 | 850 | 400 | 288 | 288 | Between every pumping stage keep 4 hour shut-in pause.
17 | 3 | 3 | 16 | 850 | 600 | 576 | 576
18 | 3 | 4 | 16 | 850 | 600 | 576 | 576 | If pressure 850 is reached or seismic activity increases
19 | 3 | 5 | 16 | 850 | 600 | 0 | 0 | go 400 l/min rate and stop if necessary.
20 | 3 | 6 | 16 | 850 | 600 | 0 | 0
21 | 3 | 7 | 16 | 850 | 600 | 0 | 0
22 | 3 | 8 | 16 | 850 | 600 | 0 | 0 | Formation leaking pressure around 400 bars when stage
23 | 3 |  | 24 | 0 | 0 | 0 | 0 | is changed.
24 | 4 | 1 | 16 | 850 | 600 | 576 | 576 | Changed to stage 4 because seismic activity increased
24 | 4 | 2 | 16 | 850 | 600 | 576 | 576 | in stage 1.
25 | 4 | 3 | 18 | 850 | 600 | 648 | 648
26 | 4 | 4 | 18 | 850 | 600 | 648 | 648 | If pressure 850 is reached or seismic activity increases
27 | 4 | 5 | 18 | 850 | 600 | 648 | 648 | go 400 l/min rate and stop if necessary.
28 | 4 | 6 | 18 | 850 | 600 | 648 | 555
29 | 4 | 7 | 18 | 850 | 600 | 648 | 648 | Formation leaking pressure around 500 bars when stage
30 | 4 |  | 24 | 0 | 0 | 0 | -16.5 | is changed.
31 | 5 | 1 | 24 | 860 | 400 | 576 | 576 | Closest stage to the liner shoe. Follow annular pressures.
32 | 5 | 2 | 24 | 860 | 400 | 576 | 576
33 | 5 | 3 | 27 | 860 | 400 | 648 | 648 | If pressure 860 is reached or seismic activity increases
34 | 5 | 4 | 27 | 860 | 400 | 648 | 648 | go 400 l/min rate and stop if necessary.
35 | 5 | 5 | 27 | 860 | 400 | 648 | 648
36 | 5 | 6 | 27 | 860 | 400 | 648 | 648 | Formation leaking pressure around 400 bars when stage
37 | 5 | 7 | 27 | 860 | 400 | 648 | 648 | is finished.
38 | 5 |  | 24 | 0 | 0 | 0 | -1166.5 | Final bleed off as long as well head pressure 0 bar
TOTAL | [5 empty] | 18384 | 16676.6

## Mitigation
| Mitigation measures | Mitigation measures | Mitigation measures
1 | None | Stop pumping | Stop pumping
2 |  | Engage pumper breaks | Engage pumper breaks
3 |  | Keep well pressurized | Keep well pressurized
4 |  | Notify ISUH | Notify ISUH and discuss possibility to depressurize the well
5 |  | Wait until well balances | Start depressurizing well slowly (max 1 bar/min)
6 |  | Continue with lower P & Q | Note flow out
7 |  |  | Stop when well head pressure 0 bar(g)
8 |  |  | Wait until permission to resume achieved
9 |  |  | Continue with lower P & Q
10